## Version
VERS | Date | Initials | Description of change
| 2016-01-29 | TVL | Added line to Lessons learned tab. No up revision to this file.
M | 2015-05-21 | JAH | Corrected Job Book Covers to use Project Name entry instead of Customer/End User/Location, multiple corrections to TOC of both Unit&Kit and Bare Unit.
L | 2015-03-18 | MCW | Updated Unit Release Checklist to move impeller mass properties, coupling and motor torsional info, and lateral and torsional analysis request tasks to "Pre Release" section (from "Post Release" section).
K | 2014-04-07 | MCW | Updated Unit and Kit Release Checklist versions to latest per C. Cornelius Update on March 21, 2014 to standalone checklist file.
J | 2014-04-04 | JDA | Added updated tabs for contract book table of contents; corrected linking issues; added release checklists; added standard work discriptions to instructions tab for TOC's, release checklists, drafting request, and lessons learned tab.
I | 2014-01-14 | TVL | Added columns to Lessons Learned Check Lists tab and to the Spec Review tab
H | 2011-12-16 | JAH | Added CONTROLS ENGINEER to job book cover. Entry already existed on the global input tab.
G | 2011-06-09 | JDA | Added TOC tab for a spec / contract book table of contents. Incorporating changes from PE meeting - In Work
F | 2011-04-29 | JDA | Update based on PE meeting discussion on 4/29/2011. Incorporation of the Job Issues Log into this sheet to keep Job information in a single place. Added Header Txt tab that will format a standard document header which is populated by the Global Input tab. Added Standard Work Instructions tab to clarify intent and use of the tool.
E | 2011-04-04 | JDA | Added conditional formatting to spec review tabs. Added descriptions / instructions to template .
D2 | 2008-08-25 | CAC | Added "RPN" Column to spec review tab, saved template with all the yellow cells you see, changed cell A1 from "Revision" to "VERS", bold column headers this sheet.
D1 | 2008-07-03 | JDA | Added Status Codes and Risk Codes to Spec Review Tab. This will give the ability to track any spec issues and assign a risk to each specification to determine the criticality of the specification and its impact on the project. Also added Detailed Guideline's tab so specs or instructions related to the specification can be referenced.
D | 2008-06-23 | JDA | Updated Approved Vendors and Utilities tabs. Spec Review Sheet added to Job Info Sheet. This sheet is a tool for PE's to track a job spec review. All customer specifications are listed here to keep data in one place. Specifications are listed by category. Job specs are compiled from oldest to newest. Starting from the PO and Material Req. and then going through the scope of supply, spec sheets, and then meeting notes/emails. This sheet is to be updated throughout the project to keep track of all specs important to the job and to have this information in one place.
C | 2008-02-07 | CAC | Added engineering job book covers. Updated vlookup() functionality w/ input sheet.
B | 2008-02-02 | CAC | Added version sheet.
A | 2008-01-03 | CAC | Preliminary revision, updated Tom Huseas sheet with Global Input sheet. Restructured lube system data sheet. Added additional items to lube system data sheet. Updated sheet headers to ref Global Input data.
Revision Suggestions:
| ??? | ??? | Review per API - 614 new version (API-614 datasheet?)
| 2008-08-25 | CAC | Create instruction sheet separate from version sheet. Include: naming conventions (distinguish between revision and version), color code (review expectations), version & revision control (review/approval process?), directory location of master template, all kinds of other crapola.
| 2008-11-20 | JH/CAC | Include Applicable Spec Review Matrix: Matrix listing applicable specifications/documentation ROWS First rows to consist of minimum documents required for project entry/release (current PO trans, Data Sheets, Scope, Select, etc) Remaining rows to be populated by any non typical APPLICABLE documents (documents formal Sundyne exception) COL Document Rev (if app, else N/A) Revision NUM/LETT (if app…) Initials of project team members - Field filled in with rev & date of document review (illustrates which docs have been reviewed)

## Std Work Instructions
Tab Name | Standard Work / Instructions
Requires Product (Kit) Engineer Attention
Requires Product (Unit) Engineer Attention
Requires Project Manager Attention
Requires Electrical/Controls Engineer Attention
Global Input: | Fill in input values as required. These will populate the text fields in the remainder of the spreadsheet. Keep this workbook saved in the job file in the engineering folder.
Header Txt: | This tab contains a standardized header text that can be used on other documentation that will be submitted to the customer. There is also a "job summary" that can be printed for quick reference to job information such as drawings numbers and work orders.
Job Book Covers: | Job information is propagated automatically from the global input sheet. Use these covers for the engineering job books as required.
Spec Book Covers: | Job information is propagated automatically from the global input sheet. Use these covers for the job specification books as required.
Book TOC: | Table of contents tabs for use in project books. Separated into different job types: Unit+Kit, Bare Unit, Unit seperate, Kit Seperate, and Spec Book. Use as required.
Release Checklists: | Unit release and Kit release checklists.
Tech Docs Index: | Put List of applicable project specs here. These should be listed in the Scope of Supply or Project PO. This can be a copy and paste from the PO or project scope of supply. This list should include all applicable specifications and the revision. Include sign off that spec was reviewed, by whom, and the date complete. List spec hierarchy. PM responsibility.
Complex Drafting Request | Tool used to communicate job requirements to design team.
Spec Review: | Copy special requirements from contract review and customer specification review here for future reference. Indicate special/problem requirements via status and risk codes to the left. (Uses conditional formatting)
Contract Issues Log: | Indicate any contract issues here. This tool should be used to indicate any problems / discrepancies that are found during the contract review and customer specification review. These issues should be communicated to the PM and resolved.
Shop & Build Issues Log: | Indicate any Shop or Build issues here. This tool should be used to document and track and issues encountered in assembly and test phase of the project. These issues should be communicated to the PM (and possibly customer) and resolved. This could also be considered the shipment punch list.
Manufactures List:
Lessons Learned: | Log any lessons learned onto this tab, add descriptions and categorize as needed. These should be logged into the seed/template file located in S:/Current Projects/New Project/Engineering to ensure that lessons learned are communicated to future users.

## Global Input
Description | Value | Comments | Reference names | Cell/Range
SUNDYNE SERIAL # : | Enter Data on Input Sheet |  | _TAB01 | B3:C53
PROJECT NAME : | Enter Data on Input Sheet
CUSTOMER : | Enter Data on Input Sheet
END USER : | Enter Data on Input Sheet
LOCATION : | Enter Data on Input Sheet
PRODUCT MODEL # : | Enter Data on Input Sheet
SERVICE : | Enter Data on Input Sheet
CUSTOMER TAG # : | Enter Data on Input Sheet
INSTRUMENT TAG PREFIX : | Enter Data on Input Sheet
QUOTATION # : | Enter Data on Input Sheet |  | Fill in values as required.
PURCHASE ORDER # : | Enter Data on Input Sheet |  | These will populate the text fields in the remainder of the spreadsheet.
PURCHASE ORDER REVISION # : | Enter Data on Input Sheet |  | Keep this workbook saved in the job file in the engineering folder.
PURCHASE ORDER REVISION DATE : | Enter Data on Input Sheet
SALES ORDER # : | Enter Data on Input Sheet
UNIT WORK ORDER # : | Enter Data on Input Sheet
COMMISSIONING SPARES WORK ORDER # : | Enter Data on Input Sheet
CAPITAL SPARES WORK ORDER # : | Enter Data on Input Sheet
UNIT LONG LEAD WORK ORDER # : | Enter Data on Input Sheet
KIT LONG LEAD WORK ORDER # : | Enter Data on Input Sheet
HORIZONTAL ASSEMBLY WORK ORDER # : | Enter Data on Input Sheet
LUBRICATION SYSTEM KIT WORK ORDER # : | Enter Data on Input Sheet
SEAL SYSTEM KIT WORK ORDER # : | Enter Data on Input Sheet
OUTLINE DRAWING : | Enter Data on Input Sheet
SCHEMATIC DRAWING : | Enter Data on Input Sheet
P&ID DRAWING : | Enter Data on Input Sheet
HORIZONTAL ASSEMBLY DRAWING : | Enter Data on Input Sheet
LUBRICATION SYSTEM KIT DRAWING : | Enter Data on Input Sheet
SEAL SYSTEM KIT DRAWING : | Enter Data on Input Sheet
BASE DRAWING : | Enter Data on Input Sheet
RESERVOIR DRAWING : | Enter Data on Input Sheet
PROJECT MANAGER : | Enter Data on Input Sheet
DOCUMENT COORDINATOR : | Enter Data on Input Sheet
UNIT PRODUCT ENGINEER : | Enter Data on Input Sheet
KIT PRODUCT ENGINEER : | Enter Data on Input Sheet
PRODUCT DESIGNER : | Enter Data on Input Sheet
CONTROLS ENGINEER : | Enter Data on Input Sheet
UNIT LONG LEAD RELEASE DATE : | Enter Data on Input Sheet | Per Planning Standard Work
UNIT RELEASE DATE : | Enter Data on Input Sheet | Per Planning Standard Work
KIT LONG LEAD RELEASE DATE : | Enter Data on Input Sheet | Per Planning Standard Work
KIT RELEASE DATE : | Enter Data on Input Sheet | Per Planning Standard Work
SHIP DATE : | Enter Data on Input Sheet | Per Planning Standard Work
XX-1 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-2 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-3 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-4 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-5 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-6 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-7 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-8 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-9 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP
XX-10 | Enter Data on Input Sheet | FUTURE USE WITH VLOOKUP

## Header Txt
DESCRIPTION / TITLE
|  |  |  | CUSTOMER : | Enter Data on Input Sheet
|  |  |  | END USER : | Enter Data on Input Sheet
|  |  |  | LOCATION : | Enter Data on Input Sheet
|  |  |  | SERVICE : | Enter Data on Input Sheet
SUNDYNE SERIAL # : | Enter Data on Input Sheet |  |  | CUSTOMER TAG # : | Enter Data on Input Sheet
PRODUCT MODEL # : | Enter Data on Input Sheet |  |  | PURCHASE ORDER # : | Enter Data on Input Sheet
Job Info Summary
|  | SUNDYNE SERIAL # : | Enter Data on Input Sheet
|  | PROJECT NAME : | Enter Data on Input Sheet
|  | CUSTOMER : | Enter Data on Input Sheet
|  | END USER : | Enter Data on Input Sheet
|  | LOCATION : | Enter Data on Input Sheet
|  | PRODUCT MODEL # : | Enter Data on Input Sheet
|  | SERVICE : | Enter Data on Input Sheet
|  | CUSTOMER TAG # : | Enter Data on Input Sheet
|  | UNIT WORK ORDER # : | Enter Data on Input Sheet
|  | COMMISSIONING SPARES WORK ORDER # : | Enter Data on Input Sheet
|  | CAPITAL SPARES WORK ORDER # : | Enter Data on Input Sheet
|  | UNIT LONG LEAD WORK ORDER # : | Enter Data on Input Sheet
|  | KIT LONG LEAD WORK ORDER # : | Enter Data on Input Sheet
|  | HORIZONTAL ASSEMBLY WORK ORDER # : | Enter Data on Input Sheet
|  | LUBRICATION SYSTEM KIT WORK ORDER # : | Enter Data on Input Sheet
|  | SEAL SYSTEM KIT WORK ORDER # : | Enter Data on Input Sheet
|  | OUTLINE DRAWING : | Enter Data on Input Sheet
|  | P&ID DRAWING : | Enter Data on Input Sheet
|  | HORIZONTAL ASSEMBLY DRAWING : | Enter Data on Input Sheet
|  | LUBRICATION SYSTEM KIT DRAWING : | Enter Data on Input Sheet
|  | SEAL SYSTEM KIT DRAWING : | Enter Data on Input Sheet
|  | BASE DRAWING : | Enter Data on Input Sheet
|  | RESERVOIR DRAWING : | Enter Data on Input Sheet
|  | UNIT LONG LEAD RELEASE DATE : | Enter Data on Input Sheet
|  | UNIT RELEASE DATE : | Enter Data on Input Sheet
|  | KIT LONG LEAD RELEASE DATE : | Enter Data on Input Sheet
|  | KIT RELEASE DATE : | Enter Data on Input Sheet
|  | SHIP DATE : | Enter Data on Input Sheet

## Job Book Covers
[6 empty] | Enter Data on Input Sheet / Enter Data on Input Sheet / Enter Data on Input Sheet | Enter Data on Input Sheet / Enter Data on Input Sheet / Enter Data on Input Sheet | Enter Data on Input Sheet / Enter Data on Input Sheet / Enter Data on Input Sheet
Enter Data on Input Sheet / Enter Data on Input Sheet / Enter Data on Input Sheet
Engineering Job Book for Order Enter Data on Input Sheet
[6 empty] | Engineering Job Book for Order Enter Data on Input Sheet | Engineering Job Book for Order Enter Data on Input Sheet | Engineering Job Book for Order Enter Data on Input Sheet
|  |  | SUNDYNE SERIAL # : | Enter Data on Input Sheet
|  |  | UNIT WORK ORDER # : | Enter Data on Input Sheet
|  |  | PURCHASE ORDER # : | Enter Data on Input Sheet
|  |  | CUSTOMER TAG # : | Enter Data on Input Sheet
|  |  | PRODUCT MODEL # : | Enter Data on Input Sheet
|  |  | SHIP DATE : | Enter Data on Input Sheet
UNIT WORK ORDER # :
[6 empty] | UNIT WORK ORDER # : |  | UNIT WORK ORDER # :
|  | Book | 1 of |  | 1
[6 empty] | Enter Data on Input Sheet | Enter Data on Input Sheet | Enter Data on Input Sheet
PURCHASE ORDER # :
[6 empty] | PURCHASE ORDER # : |  | PURCHASE ORDER # :
[6 empty] | Enter Data on Input Sheet | Enter Data on Input Sheet | Enter Data on Input Sheet
CUSTOMER TAG # :
[6 empty] | CUSTOMER TAG # : |  | CUSTOMER TAG # :
[6 empty] | Enter Data on Input Sheet | Enter Data on Input Sheet | Enter Data on Input Sheet
PRODUCT MODEL # :
[6 empty] | PRODUCT MODEL # : |  | PRODUCT MODEL # :
PROJECT MANAGER : |  |  | Enter Data on Input Sheet
DOCUMENT COORDINATOR : |  |  | Enter Data on Input Sheet |  |  | Enter Data on Input Sheet | Enter Data on Input Sheet | Enter Data on Input Sheet
UNIT PRODUCT ENGINEER : |  |  | Enter Data on Input Sheet
KIT PRODUCT ENGINEER : |  |  | Enter Data on Input Sheet
PRODUCT DESIGNER : |  |  | Enter Data on Input Sheet
CONTROLS ENGINEER : |  |  | Enter Data on Input Sheet
[6 empty] | SHIP DATE : | SHIP DATE : | SHIP DATE :
[6 empty] | Enter Data on Input Sheet | Enter Data on Input Sheet | Enter Data on Input Sheet
[6 empty] | Book | Book | Book
14845 WEST 64th AVENUE ▪ ARVADA, COLORADO 80007 USA ▪ 303-425-0800 ▪ FAX: 303-425-0869 ▪ www.sundyne.com
[6 empty] | 1 of 1 | 1 of 1 | 1 of 1
Sundyne Corporation
Sundyne Corporation
Sundyne Corporation
Sundyne Corporation

## Spec Book Covers
| Spec Book |  |  | Spec Book | Spec Book | Spec Book
Specification Book for Order Enter Data on Input Sheet, Enter Data on Input Sheet
|  |  |  | Specification Book for Order Enter Data on Input Sheet, Enter Data on Input Sheet | Specification Book for Order Enter Data on Input Sheet, Enter Data on Input Sheet | Specification Book for Order Enter Data on Input Sheet, Enter Data on Input Sheet
|  | Book 1 of | 1
14845 WEST 64th AVENUE ▪ ARVADA, COLORADO 80007 USA ▪ 303-425-0800 ▪ FAX: 303-425-0869 ▪ www.sundyne.com
|  |  |  | Book 1 of 1 | Book 1 of 1 | Book 1 of 1
Sundyne Corporation

## Unit&Kit Book TOC
PRODUCT ENGINEERING NOTEBOOK - UNIT & KIT
TABLE OF CONTENTS
S/N: | Enter Data on Input Sheet | PROJECT: | Enter Data on Input Sheet
MODEL: | Enter Data on Input Sheet | PRODUCT ENGINEER: | Enter Data on Input Sheet
DESCRIPTION
1 | Correspondence, Meeting Notes, Internal Emails
2 | As-Sold Scope of Supply, Quotation Data, P&ID, Outline Drawing
3 | Purchase Order, PO Transmittal, Pricing
4 | API 617 Datasheets, Engineering Run / Stage Sizing
5 | Project Schedule, Documentation List
6 | OP 20 Text, Quality Control Plan, JDE Line Items, Order Text
7 | Unit BOM
8 | Unit Long Lead BOM
9 | Spares BOM(s), Ship Loose, Toolkit
10 | Process Seals
11 | Gearbox Engineering, Gearbox Module Pick, Drawings
12 | Compressor End Engineering, Process End Module Picks, Drawings
13 | Analysis Reports
14 | Motor Data, Coupling Data
15 | Kit BOM
16 | Kit Long Lead BOM
17 | API 614 Datasheets
18 | Lube System - Oil Cooler, Filters, Valves, etc.
19 | Seal System - Filters, Valves, etc.
20 | Electrical Instrumentation - Transmitters, J-boxes, etc.
21 | Outline Drawings, Schematic Drawings, Kit Drawings
22 | Customer Specifications
23 | Process Procedures/Info & PFD
24 | Process P&ID's
25 | Control Panel, Process Control Valves, Process Components
26 | Assembly & Testing History and Records
27 | Vendor/Manufacturing Issues, Supplier Deviations, NCMs
28 | Similar Job Information
29 | Instruction Manual
30 | Final Data
31 | Unit Installation , Commissioning & Field Service Reports
DRAWINGS:

## Bare Unit Book TOC
PRODUCT ENGINEERING NOTEBOOK - BARE UNIT
TABLE OF CONTENTS
S/N: | Enter Data on Input Sheet | PROJECT: | Enter Data on Input Sheet
MODEL: | Enter Data on Input Sheet | PRODUCT ENGINEER: | Enter Data on Input Sheet
DESCRIPTION
1 | Correspondence, Meeting Notes, Internal Emails
2 | Quotation Data, Scope of Supply, Pricing
3 | Purchase Order, PO Transmittal
4 | API 617 Data Sheets, Stage Sizing, Performance Curves
5 | Schedule, Release Checklist, Documentation List/VDI
6 | SO Line Items, OP 20 Text
7 | Unit BOM
8 | Long Lead BOM
9 | Spares BOM, Toolkit
10 | Bare Unit Outline and Kit Drawings, Drafting Request
11 | Gearbox and Coupling Design, Gearbox Module Picks, Drawings
12 | Compressor End Design, Process End Module Picks, Drawings
13 | Process Seals
14 | Customer Outline, Kit, System drawings
15
16
17
18 | Motors
19 | Lube Oil Cooler
20 | Electrical Instrumentation (Transmitters, Switches, etc.)
21 | Analysis Reports
22 | Sundyne Quality Plan
23 | Vendor/Manufacturing Issues, Supplier Deviations, Clinics, NCMs
24 | Assembly & Testing History and Records
25 | Instruction Manual
26 | Customer/End User Specifications
27 | Similar Job Information
28 | Root Cause Analysis, Failure Investigations
29 | Final Data
30 | Unit Installation , Commissioning & Field Service Reports
31
DRAWINGS:

## Unit Book TOC
PRODUCT ENGINEERING NOTEBOOK - UNIT
TABLE OF CONTENTS
S/N: | Enter Data on Input Sheet | PROJECT: | Enter Data on Input Sheet
MODEL: | Enter Data on Input Sheet | PRODUCT ENGINEER: | Enter Data on Input Sheet
DESCRIPTION
1 | Correspondence, Meeting Notes, Internal Emails
2 | Quotation Data, Scope of Supply, Pricing
3 | Purchase Order, PO Transmittal
4 | API 617 Data Sheets, Stage Sizing, Performance Curves
5 | Schedule, Release Checklist, Documentation List/VDI
6 | SO Line Items, OP 20 Text
7 | Unit BOM
8 | Long Lead BOM
9 | Spares BOM, Toolkit
10 | Bare Unit Outline and Kit Drawings, Drafting Request
11 | Gearbox and Coupling Design, Gearbox Module Picks, Drawings
12 | Compressor End Design, Process End Module Picks, Drawings
13 | Process Seals
14 | Seal System
15 | Lube System
16 | Baseplate Design
17 | Control Panel, Process Control Valves, Process Components
18 | Motors
19 | Lube Oil Cooler
20 | Electrical Instrumentation (Transmitters, Switches, etc.)
21 | Analysis Reports
22 | Sundyne Quality Plan
23 | Vendor/Manufacturing Issues, Supplier Deviations, Clinics, NCMs
24 | Assembly & Testing History and Records
25 | Instruction Manual
26 | Customer/End User Specifications
27 | Similar Job Information
28 | Root Cause Analysis, Failure Investigations
29 | Final Data
30 | Unit Installation , Commissioning & Field Service Reports
31
DRAWINGS:

## Kit Book TOC
KIT PRODUCT ENGINEERING NOTEBOOK
TABLE OF CONTENTS
S/N: | Enter Data on Input Sheet | PROJECT: | Enter Data on Input Sheet
MODEL: | Enter Data on Input Sheet | PRODUCT ENGINEER: | Enter Data on Input Sheet
DESCRIPTION
1 | Correspondence, Meeting Notes, Internal Emails
2 | Scope of Supply, Quotation Data, P&ID, Outline Drawing
3 | Purchase Order, PO Transmittal, Pricing
4 | API 617 Datasheets, Engineering Run / Stage Sizing
5 | Project Schedule, Documentation List
6 | OP 20 Text, Quality Control Plan, JDE Line Items, Order Text
7 | Unit BOM
8 | Unit Long Lead BOM
9 | Spares BOM(s), Ship Loose, Toolkit
10 | Process Seals
11 | Gearbox Engineering, Gearbox Module Pick, Drawings
12 | Compressor End Engineering, Process End Module Picks, Drawings
13 | Analysis Reports
14 | Motor Data
15 | Kit BOM
16 | Kit Long Lead BOM
17 | API 614 Datasheets
18 | Lube System - Oil Cooler, Filters,
19 | Seal System -
20 | Electrical Instrumentation (Transmitters, etc.)
21
22
23
24
25 | Control Panel, Process Control Valves, Process Components
26 | Assembly & Testing History and Records
27 | ACE Turnbacks, Mistake Proofs, etc.
28 | Similar Job Information
29 | Instruction Manual
30 | Final Data
31 | Unit Installation , Commissioning & Field Service Reports
DRAWINGS:

## Unit Engineering Checklist
RELEASE CHECKLIST - PINNACLE UNITS |  |  |  |  | Rev 03/21/2014
PROJECT: |  |  |  | UNIT WO #:
UNIT PRODUCT ENGINEER: |  |  |  | SPARES WO #:
| DATE |  |  | LL WO #:
PRE RELEASE
RECEIVE CONTRACT & SCOPE DOCUMENTS
SPECIFICATION REVIEW (DOCUMENT IN JOB REQUIREMENTS & BUILD ISSUES LOG)
OBTAIN AERO BOM FROM AERO ENG
COMPLETE LEVEL I SCREENING TOOL
COMPLETE GEARBOX BUILDSHEET
PUMP-OUT VANE TRIM SPREADSHEET
AERO THRUST SPREADSHEET: GEAR HELIX ANGLES, THRUST BEARING CAPACITIES
GEARBOX LOSS / OIL FLOW SPREADSHEET: CONFIRM DATA SHEET LOSSES, SELECT MLOP
DETERMINE O-RING MATERIAL, DOCUMENT FINDINGS
CREATE SEAL I/M TEXT, SEND SEAL RFQ TO VENDOR
CREATE AS-PURCHASED API DATA SHEET FOR SUBMITTAL
DETERMINE LONG LEAD PART NUMBERS (GBOX, 3 CASTINGS PER STAGE, SEALS, SHAFTS, BEARINGS, IMP SLUGS (A/R), MLOP)
CREATE LONG LEAD ITEM MASTERS
|  | LOAD LONG LEADS (INCLUDING SPARES) & NOTIFY PLANNER |  |  |  | (LL Release)
REQUEST IMPELLER MASS PROPERTIES FROM DESIGNER
OBTAIN MOTOR SHAFT & COUPLING TORSIONAL DATA FROM PROJECT MANAGER/KIT ENGINEER
SUBMIT LATERAL ANALYSIS REQUEST
SUBMIT TORSIONAL ANALYSIS REQUEST
CREATE MODULE STRINGS USING THE STRING SELECTOR TOOL
RUN MODULE STRINGS AND CREATE BOM TEXT FILES
EDIT BOM TEXT FILE AS REQUIRED
GIVE COPY OF WO PARTS LIST TO CAD (TIM IGOE)
LOAD BOM INTO UNIT WO (AND SPARES)
FILL OUT MFG ENG NEW PARTS SHEET (R:\TRANSFER\Renae Peterson\PM's parts to process)
CREATE CG OP20/40 TEXT USING TEMPLATE, LOAD INTO UNIT WO
LOAD SPARES INTO SPARES WO
50% DESIGN REVIEW (Milestone 1)
|  | SEND UNIT RELEASE EMAIL TO M.E. |  | (Unit Release)
REVIEW UNIT AND PIECE PART ROUTINGS PRIOR TO ME RELEASE
POST RELEASE
REVIEW/COMPLETE ALL BUILD/TEST QUALITY DOCS AND ISO FORMS IN CQS AFTER ME RELEASE
REVIEW & APPROVE LATERAL & TORSIONAL ANALYSES
CHECK CROSSOVER SPOOL DRAWINGS
DEFINE PINNACLE TOOL KIT PART NUMBER, PROVIDE TO KIT ENGINEER/DESIGNER
CREATE RECOMMENDED SPARES DOCUMENT FOR SUBMITTAL
CREATE ASSEMBLED COMPRESSOR LEAK TEST PROCEDURE
FINAL DATA - CREATE ELECTRONIC BUILD SHEETS
FINAL DATA - CREATE FINAL UNIT BOM, RECOMMENDED SPARES
FINAL DATA - UPDATE IMPELLER ITEM MASTERS TO FINAL TRIM
FINAL DATA - CREATE AS-BUILT API DATA SHEET
FINAL DATA - IOM REVIEW (SPECIAL INSTRUCTIONS IF NEEDED)
FINAL DATA - CHECK OF FINAL DATA BOOKS

## Kit Engineering Checklist
RELEASE CHECKLIST - (PINNACLE/API BMC/HMP) KITS |  |  |  |  | Rev. | 2014-03-21
PROJECT: |  |  |  | UNIT WO #:
KIT PRODUCT ENGINEER: |  |  |  | HA WO #:
| DATE |  |  | KIT SPARES WO #:
KIT LL WO #:
PRE RELEASE
Receive contract and scope documents from PM (Verify PM deliverables have been meet.)
Contract/Scope Review Completed (Initial & Date for each document reviewed in Job Requirements & Build Issues Log)
Project team kick-off meeting (PM to initiate and schedule)
Spec review and populate spec review tool (Initial & Date for each document reviewed in Job Requirements & Build Issues Log)
Submit Drafting Request
Review ITP
Preliminary P&ID and GA drawing. Review and mark-up proposal drawings for first submittal to customer
Size Lube Oil Heat Exchangers
Review Main Motor/Turbine quote, drawings, and datasheets. Provide Certified Drawing to to Designer.
Select Transfer Valve (water cooled heat exchangers only)
Size Auxilliary Lube Pumps
Size Recycle and/or Throttle Valves (if required)
Size Blower and Blower Motor if Required (for noise enclosures requireing forced air cooling only)
Size Lube Pump Motors, Couplings, & Adapters
Size Lube Filters
Size Main Coupling
Select Lube Oil Regulators or Control Valves
Select Seal System Regulators or Control Valves
Size Seal Filters
Size Lube Oil Reservoir Heater
Size Seal Gas Heater (if required)
Size Accumulator or Run Down Tank (if required)
Select Thermostatic and Pressure Relief Valves (lube system)
50% Design Review (Milestone 1)
Create Kit LL Item Masters (where required)
|  |  | Load Kit LL's into WO and notify planning (AUX LOP motor, LO pump, filters (lube and seal), regulators, AMOT valve, etc.) |  |  |  | (LL Release)
Provide Designers with drawings for LL Components (as required)
Orifice Sizing (lube and seal system)
Select Gauges (lube, seal, process)
Complete Instrument Data Sheets
Define transmitters and other instrumentation (lube, seal, process)
Engineer Remaining Major Component BOM Items and provide to Kit Designer
90% Design Review (Milestone 2)
Load HA OP20/40 into WO
Load Spares Item Masters in Spares WO
Review and Approve Kit Drawings (lube, seal, hardware, horizontal assembly, electrical)
|  |  | Load HA BOM into JDE and Notify Planning and Designers |  |  | (Kit Release)
POST RELEASE
Load Ship Loose Text into JDE
Complete Analysis Request Forms (When Required - seismic/wind/lifting or skid design)
Provide Input to Cause and Effect Document
Complete API 614, and 671 Data Sheets (as required)
Complete all ISO docs in CQS following ME release (cleanliness, lube functional, hydro, seal integrity test)
Create lube system test plan (P&ID mark up)
Create seal system test plan (P&ID mark up)
Approve As-Built drawings & datasheets
Review Final Data
References:
Paul Boots Flowvision Kit Process:
R:\pumps\Flowvision Nov 2010\Std Work Praesto Kit Engineering.xlsx
Location of Standard Works for Component Sizing:
S:\Standard Work\Product Engr
Location of this document
S:\Product Engr\Tools\Pinnacle Tools
Note on E22: Be sure to calculate bore size at the quoting phase.

## Spec TOC
CONTRACT / SPECIFICATION NOTEBOOK
TABLE OF CONTENTS
Enter Data on Input Sheet, Enter Data on Input Sheet |  |  | Tab Control: | letter
TAB | DOCUMENT / SPEC | DESCRIPTION | letter | number
A |  |  | A | 1
B |  |  | B | 2
C |  |  | C | 3
D |  |  | D | 4
E |  |  | E | 5
F |  |  | F | 6
G |  |  | G | 7
H |  |  | H | 8
I |  |  | I | 9
J |  |  | J | 10
K |  |  | K | 11
L |  |  | L | 12
M |  |  | M | 13
N |  |  | N | 14
O |  |  | O | 15
P |  |  | P | 16
Q |  |  | Q | 17
R |  |  | R | 18
S |  |  | S | 19
T |  |  | T | 20
U |  |  | U | 21
V |  |  | V | 22
W |  |  | W | 23
X |  |  | X | 24
Y |  |  | Y | 25
Z |  |  | Z | 26
AA |  |  | AA | 27
AB |  |  | AB | 28
AC |  |  | AC | 29
AD |  |  | AD | 30
AE |  |  | AE | 31
AF |  |  | AF | 32
AG |  |  | AG | 33
AH |  |  | AH | 34
AI |  |  | AI | 35
AJ |  |  | AJ | 36
AK |  |  | AK | 37
AL |  |  | AL | 38
AM |  |  | AM | 39
AN |  |  | AN | 40
AO |  |  | AO | 41
AP |  |  | AP | 42
AQ |  |  | AQ | 43
AR |  |  | AR | 44
AS |  |  | AS | 45
AT |  |  | AT | 46
AU |  |  | AU | 47
AV |  |  | AV | 48
AW |  |  | AW | 49
AX |  |  | AX | 50
AY |  |  | AY | 51
AZ |  |  | AZ | 52

## Tech Docs Index
Put List of applicable project specs here. These should be listed in the Scope of Supply or Project PO.
This can be a copy and paste from the PO or project scope of supply.
This list should include all applicable specifications and the revision.
| Precedence | Specification Hierarchy
1
2
3
4
5
DATE WHEN INITIAL REVIEW WAS COMPLETE
PROVIDED? | SPEC # | SPEC TITLE / DESCRIPTION | SPEC REV | SPEC DATE | PM | UNIT PE | KIT PE | PD | CE

## Spec Review
Status Code | Category / Component | Sub Category | Risk Code | Who needs to know? AE, CE, DE, PE, PM, QE? | Description | Comments | Source | Rev | Source Location | RPN
1 |  |  | 1 |  | Copy special requirements from contract review and customer specification review here for future reference. |  |  |  |  | 1
2 |  |  | 2 |  | <---- Indicate special/problem requirements via status and risk codes to the left. (Uses conditional formatting) |  |  |  |  | 4
3 |  |  | 3 | [6 empty] | 9
Note on A1: Status Codes: 1: Design Fixed / Information Only / Closed Issue 2: Need Verification / Need Clarification (PM) / Open Issue 3: Addition/Change Order* / Urgent Open Issue *Status 3 requires approval as it will impact cost and delivery. (Show Stopper - Needs Resolution ASAP)
Note on B1: Lube System Seal System Unit Testing Main motor Lube Oil Motor Lube pump Accumulator Transmitter Instrumentation Gauge Thermowell Lube oil filter Seal gas filter Ball valve Gate valve Control valve Pressure relief valve Check valve Needle valve Flow orifice Piping Tubing Flow gage Coupling Reservoir Gage board Lube oil heater Level gauge Engineering Units Demister Y-strainer Skid Design Vibration
Note on D1: Risk Codes: 1: Standard Requirement / Information Only (Low Risk) 2: Special Requirements (Medium Risk) 3: High Impact / Impracticable (High Risk)
Note on E1: AE - Application Eng CE - Control Eng DE - Design Eng PE - Product Eng PM - Project manager QE - Quality Eng

## 50% Review MoM
50% Design Review Meeting
Project Serial Number / Name:
Reference PM-07-02-18 "Milestone Reviews for Complex Projects"
Meeting Date:
Attendees:
Item # | Status | Priority | Date Entered | Topic / Issue | Action By? | Resolution / Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
Note on B7: Open / Closed?
Note on C7: Priorities: 0:Closed / Information Only 1:Low 2:High (Need Answer Now)

## 90% Review MoM
90% Design Review Meeting
Project Serial Number / Name:
Reference PM-07-02-18 "Milestone Reviews for Complex Projects"
Meeting Date:
Attendees:
Item # | Status | Priority | Date Entered | Topic / Issue | Action By? | Resolution / Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Note on B7: Open / Closed?
Note on C7: Priorities: 0:Closed / Information Only 1:Low 2:High (Need Answer Now)

## Complex Drafting Request
Complex Project Drafting Request
Serial Number: | Enter Data on Input Sheet
Project: | Enter Data on Input Sheet
Kit Product Engineer: | Enter Data on Input Sheet
Product Designer: | Enter Data on Input Sheet
Revision Date:
Requirement | Description | Source | Rev | Comments
Material Sourcing
AML or PML
NACE - Detail scope and boundaries
Material Certs - Type and applicable components
CRNs (Canadian Registration Number) or other Regional Code requirement
Specialty Tube Fittings (Parker, etc.)
Sourcing Code per PM-07-02-08 and Sourcing Restrictions (No Chinese, India, Eastern Block mat'l, etc.)
Certification Code per PM-07-02-08, or other special certs (EN10204)
Electrical/Instrumentation
Area Classification
IP Rating
Additional Certifications (CCOE, Inmetro, etc.)
Conduit or Cable & Tray - specific requirements
Grounding requirements
Start/Stop or Control Panel on Skid
Calibration Requirements
Dial Size- 4.5" typical
Thermowells (Straight/Tapered/Van Stone & Minimum Pipe Diameter)
Base & Reservoir
Sloped Deck, Grating & Non-slip requirements
SST Gauge Board, Sun Shade, Other special requirements
Reservoir Size and Material
Piping System
Tube or Pipe - if pipe define Weld Type, Schedule, Flange Rating
Flange Kit and Gasket (material, coatings, gasket type)
Other
Noise Enclosure - if yes define type
Process Equipment by Sundyne (recycle valve, instruments, suction strainer, etc)
Suction Spools
Companion Flanges - if yes what material
Heat Tracing and Insulation
Paint Requirements or Special Coatings
Low/High Temperature Requirements (process or ambient). Hot boxes needed for instruments?

## Contract Issues Log
Item # | Status | Priority | Date Entered | Issue | Source | Rev | Location | Action By? | Resolution / Comments
1 | Open | 0 |  | Indicate any contract issues here. This tool should be used to indicate any problems / discreprencies that are found during the contract review and customer specification review. These issues should be communicated to the PM and resolved.
2 | Closed | 1 |  | Do not use this tool for shop / build issues. Use the Shop & Build issues log.
3 |  | 2
Note on B1: Open / Closed?
Note on C1: Priorities: 0:Closed / Information Only 1:Low 2:High (Need Answer Now)

## Shop & Build Issues Log
Item # | Status | Priority | Date Entered | Issue | Action By? | Status / Resolution / Comments
1 | Open | 0 |  | Indicate any Shop or Build issues here. This tool should be used to document and track and issues encountered in assembly and test phase of the project. These issues should be communicated to the PM (and possibly customer) and resolved. This could also be considered the shipment punch list.
2 | Closed | 1 |  | Do not use this tool for spec or contractual issues. Use the contract issues log.
3 |  | 2
Note on B1: Open / Closed?
Note on C1: Priorities: 0:Closed / Information Only 1:Low 2:High (Need Answer Now)

## Manufacturer's List
Sundyne Standard Manufacturer's List
|  | CUSTOMER : | Enter Data on Input Sheet
|  | END USER : | Enter Data on Input Sheet
|  | LOCATION : | Enter Data on Input Sheet
|  | SERVICE : | Enter Data on Input Sheet
SUNDYNE SERIAL # : | Enter Data on Input Sheet | CUSTOMER TAG # : | Enter Data on Input Sheet
PRODUCT MODEL # : | Enter Data on Input Sheet | PURCHASE ORDER # : | Enter Data on Input Sheet
Category | Vendor(s)
Main Motor
Lube Pump
Aux Lube Pump Motor
Process Seals
Bearings
Spacer Coupling
Main Drive Coupling
LO Heat Exchanger
Oil Filter
Gas Filter
Knock-Out Pot
Pressure Trans (Differential)
Pressure Switch (Low Range)
Pressure Gauge (Gage)
Pressure Gauge (Differential)
Instrument Manifolds
Orifice Runs
Flow Indicator
Temp Trans
Temp Gauge
Level Transmitter
Level Gage, Glasses & Cocks
Radial, Axial Probe / Key Phaser
RTDs
Anti-Surge Controller
Vib / Temp Monitor
PLC
Operator Terminal (HMI)
Safety Barriers
Cable Instrument (Special Purpose)
Cable Tray
Cable Hubs
Terminals
Control Panel Encl.
Junction Boxes
Pressure Safety Relief Valves
Regulator, Pressure, Self Actuated
Regulator, Temp, Self Actuated
Valves, Ball, etc
Process Valve/ By-pass/ Control

## Lessons Learned Check Lists
Who needs to know? AE, CE, DE, PE, PM, QE? | Category | Sub-category | Gotcha - What to check for: | Comments | Source | Rev | Source Location
| Base |  | Piping and Tubing Supports (Unistrut mounting blocks inside & out, 1/4-20 thread tap size)
| Base |  | Make sure the piping support mounting blocks don't sit above jack screw locations.
| Base |  | Piping suport mounting blocks must stick out far enough for pipe flanges.
| Base |  | Verify sizes of access and clearance holes through sides of skids.
| Base |  | Check that access penetrations are above the drain pan in the lube system pit area.
| Base |  | SST Drain Piping on Pinnacles (from Unit Pedestal - Requires 309L filler weld rod called out in drawing notes).
| Base |  | Call out "CJP" (Complete Joint Penetration) in welding symbols for Drain Piping. Verify full penetration welds on drain.
| Base |  | Include the Earthing/Grounding features (SST Pad with two tapped holes - check size).
| Base |  | Verify holes in pedestal line up with holes in HMP gear box.
| Base |  | Verify base machining callouts for level and flatness.
| Base |  | Chamfer gearbox mounting holes for gearboxes.
| Base |  | Use correct gearbox mounting kit AT01GC02 (not AT01GC03 or AT01GC01)
| Base |  | Pinning the Pinnacle Gearbox on 4-stage machine can't be done if cases are installed. Try to have pinning done before building the unit. Same for HMP 3000's & 5000's.
| Base |  | Check grouting holes and grouting vent holes. Verify grout hole is present in motor pedesal mounting plate. Lips may required on vent holes.
| Base |  | Max width & height of skid for internal assembly is … TBD
| Motors |  | Make your own shaft keys
| Motors |  | Put Junction boxes on top for Lube Pump Motors if permitted (std).
| Motors |  | Small style D flanges preferred for Lube Pump Motors (NEMA motors)
| Motors |  | Check the PM's motor quotes for: Item Master Text Vibration &/or Temp Probes Bearing Type
Motors
| Lube Kits |  | Lapped flanges require longer studs in the flange kit than standard flanges.
| Lube Kits |  | Verify drain line CAN be installed through the motor pedestal. Consider locations of flange breaks.
| Lube Kits |  | Check elbows in piping exist in design. 3/4" may be the limit of what the shop can bend.
| Lube Kits |  | Verify piping schedules match.
| Lube Kits |  | Check if there is a special material composition requirement for tubing. E.g. 316 SST with minimum 2.5% Molybdenum content and max 80 HRB hardness.
| Lube Kits |  | Check if there is a requirement on dual element temperature sensors for thermowells. The transmitter, temperature sensor assembly, and cable between the sensor and transmitter all need to be configured as such.
| Seal System Kits |  | Check if there is a special material composition requirement for tubing. E.g. 316 SST with minimum 2.5% Molybdenum content and max 80 HRB hardness.
Seal System Kits
Seal System Kits
Seal System Kits
Seal System Kits
Seal System Kits
| HA Drawing |  | Check nameplate requirements for "phenolic" and "3 layer". Verify that Artcraft is going to supply phenolic and not Rowmark. Specify layer colors (e.g. white/black/white).
DE, PE | HA Drawing |  | Check gearbox coupling key is sized to match coupling hub (full key matches the coupling hub length, steps down to match shaft diameter outside of coupling hub.)
HA Drawing
HA Drawing
HA Drawing
HA Drawing
| NDE |  | Check for special requirements on Material Traceability, Weld Maps, PMI, etc, and how it relates to NDE on both the support systems and Unit.
| Electrical Kits |  | Communicating flex condiut length restrictions (e.g. <2 feet). Put on drawing, in routing, talk to the electricians?
| NDE |  | Check for special requirements on Material Traceability, Weld Maps, PMI, etc, and how it relates to NDE on both the support systems and Unit.
PM, PE | Motors | Bechtel General Spec | 2.1.1.1 Addition: The compressor shall also be suitable for continuous operation at any capacity between lowest specified flow and 110% of the guaranteed flow. The guaranteed capacity shall be at least 20% greater than the predicted surge capacity. The stonewall capacity is defined as the capacity where the decrease in polytropic head is 10% for an increase of 1% in inlet volume flow. The stonewall flow shall be at least 110% of the rated flow at rated speed. The Seller shall confirm the suitability of the compressor to operate continuously at the stonewall point. In addition, any limitation to operate beyond the stonewall point shall be identified. | Make sure this is well understood when sizing the main motor. The main motor must be large enough to reach stonewall. | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE, PM, PE | Seal System Kits | Bechtel General Spec | 2.1.1.4 Addition: The Seller shall be responsible for determining the thermodynamic properties of the gases to be compressed based on the gas analysis data specified on the Project data sheets. Supplier shall specify the equations of state used for the calculations. | We should take exception to this. The process licensor should be responsible for the thermodynamic properties of the gases | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
PE, PM | Testing | Bechtel General Spec | 2.2.1.15.5 Addition: Impact test of casing and connections welded to the casing shall be conducted in accordance with ASME Section VIII, Div.1, UG-84. The impact tests of impellers and shafts shall be conducted in accordance with following requirements: Three measurements shall be carried out at the minimum operating temperature. The average impact values shall be greater than 20.33 N-m (15 ft-lb) and minimum value shall be greater than 16.26 N-m (12 ft-lb). | Add to the ITP | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE | Compressor Unit | Bechtel General Spec | 2.3.2.1.6 Drains must be provided as required to drain completely the compressors and seal housings. | Pinnacle seal housings do not allow for complete draining. Is this a standard exception? | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE | Seal System Kits | Bechtel General Spec | 2.8.1.7 Decision: The Seller has complete unit responsibility for the Dry Gas Seal System. Refer to Project Specification 3PS-MCCS-F0002, API Dry Gas Seal Systems and the data sheets. | This may include seal gas heaters to maintain dew point margin. What does 3PS-MCCS-F0002 say? | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE, PM, PE | Seal System Kits | Bechtel General Spec | 2.8.4.1 Addition: The Buyer shall provide gas compositions, pressures, and temperatures for all cases. The Seller shall advise if coalescing filters, heat tracing and/or insulation is required. A phase diagram showing gas dew point curves for the specified start-up, operating and shutdown gas compositions shall be provided by the Supplier for all operating cases. Hydrate formation shall be considered for the entire seal gas system. | The gas dew points are independent of seal system design. The dew point curve should be supplied by the process licenser. Sundyne should take exception to supplying this. (Buyer should provide us with the dew point curve. Once we have the dew point curve we can analyze our system to determine dew point temperature margin.) | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE | Coupling | Bechtel General Spec | 3.2.2 Addition: The coupling guard shall be provided with an oil drain line. The coupling drain shall be led to lube oil return line and shall be provided with a sight glass. | We do not use couplings that require oil spray. However this requirement was not taken exception to. Take exception to the coupling guard needing an oil drain and take exception to the coupling guard needing to be sealed. | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
DE, PE | Skid Design | Bechtel General Spec | 4.2.5 Addition: A non-slip grating (with serrated surface) shall cover all walkway or maintenance areas. In no circumstance shall the lube oil piping and components create tripping hazards to locations where routine maintenance is required. | items that require regular maintenance are: control valves, pressure relief valves, pumps, and motors. | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems
AE, DE | Skid Design | Bechtel General Spec | 3.3.2.4 Decision: Any location where personnel may be expected to walk and/or work shall have non-skid walking surfaces (steel serrated grating). Horizontal decked surfaces shall be sloped to avoid the collection of water. | A sloped deck and serrated grating adds significant design time. Cost adder. | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE, DE, PE | Skid Design | Bechtel General Spec | 3.3.2.6 Decision: The baseplate shall be designed to facilitate the use of optical, laser or other instruments for field leveling during installation. | It would be beneficial for us to add design features that would allow for field leveling without removing the main motor or compressor. | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE | Skid Design | Bechtel General Spec | 3.3.2.9 Decision: The bottom of the baseplate shall have machined mounting pads. | Take exception. We use leveling screws to level the skid. In the field skids are set on concrete pads that have had their top surface chipped/hammered (per API) so that a stronger bond is created when grouted. | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
DE, PE | Tubing | Bechtel General Spec | 2.9.1.3 Tube fittings shall be Swagelok. | This needs to be communicated with purchasing. | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE | Vibration System | Bechtel General Spec | 3.4.7.9 New Paragraph: Leads from the vibration probes shall be designed and installed to eliminate noise pickup and signal deterioration and shall be brought out to terminal boxes mounted on the skid edge. All wiring shall be armored cables with cable gland provided in each terminal. Each probe shall be completed with an individual proximitor mounted in a terminal box. | I don't believe Bentley has cable glands for their armored cables. | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
AE | Vibration System | Bechtel General Spec | 3.4.7.10 New Paragraph: A keyphasor probe shall be supplied for each rotating shaft (i.e. one for each bull gear shaft and each pinion gear shaft). | Do we have the capability to put a keyphasor on the bullgear? | 25798-200-3PS-MCCS-F0001 Project Specification for API 617 Integrally Geared Compressors | 000
DE, PE | Lube Oil System | Bechtel General Spec | All piping to be dual grade stainless steel 316/316L |  | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
DE, PE | Lube Oil System | Bechtel General Spec | Minimum tubing size is 3/8" (10mm) (except inside control panels, 1/4" permitted) |  | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
AE | Lube Oil System | Bechtel General Spec | 5.1.4 Modification: The Seller shall supply interconnecting piping between multiple baseplate skid units. Buyer shall supply interconnecting piping to/from remote air-cooled lube oil coolers. Seller shall provide lube oil temperature control valve installed on the Mineral Lube Oil console. | We do not want to supply interconnection piping between multiple skids. This would have to be done in the field for a proper fit, and therefore would be very expensive. Take exception. | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
DE, PE | Lube Oil System | Bechtel General Spec | Slip-on flanges are not acceptable. |  | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
DE, PE | Lube Oil System | Bechtel General Spec | 5.1.10 Only Vent and Drain lines can have socket-weld fittings. |  | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
CE, DE, PE | Lube Oil System | Bechtel General Spec | 5.3.2 Quarter inch (1/4”) type instrument valves with 6.35 mm (1/4”) block- and- bleed valves are acceptable for the synthetic lube oil system only. Transmitters shall not be located more than 600 mm (2 ft) from the sensing point. | It will be very difficult to maintain 2ft or less from the sensing point. Take exception. | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
CE | Instrumentation | Bechtel General Spec | 6.1.4 Addition: All terminal or junction boxes and associated hardware shall be Stainless Steel 316L. Typical hardware items are: hinges, bolts, nuts, latches, washers, rivets, locks and handles, etc. |  | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
DE, PE | Skid Design | Bechtel General Spec | 6.3.1.4 Modification: All gauge boards and Dry Gas Seal panels framework and panel faces shall be Stainless Steel 316L construction. | This was a requirement on the Wheatstone job and it was not painted. Cost adder. | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
PE, PM | Lube Oil System | Bechtel General Spec | 7.2.2.2.1 Testing: Ten percent (10%) of all lube oil piping with both weld and material traceability is required. |  | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
AE, PE | Lube Oil System | Bechtel General Spec | 4.1.7 Gas Turbine driven equipment will have separate synthetic and mineral lube oil systems. | extra design costs | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
PE | Lube Oil System | Bechtel General Spec | 4.6.1.5.h&i Filter housings shall be of welded and bolted Stainless Steel 316L construction. Inlet and outlet connections shall be flanged. Screw type head-to-body connections are not permitted. Filter Housings require an ASME Section VIII Stamp. |  | 25798-200-3PS-MCCS-F0003 Project Specification for API Special Purpose Lubrication Systems | 000
Note on A1: AE - Application Eng CE - Control Eng DE - Design Eng PE - Product Eng PM - Project manager QE - Quality Eng